## Sprint 1
Hours Spent
|  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Story 8 | 14.5 | 0 | 2 | 4 | 0 | 2.5 | 0 | 2 | 1 | 0 | 3 | 14.5
Story 9 | 7.5 | 0 | 0 | 0.5 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 7.5
Story 10 | 6.5 | 0 | 2 | 0 | 3 | 0 | 1.5 | 0 | 0 | 0 | 0 | 6.5
Story 11 | 6.5 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 2 | 2 | 6.5
Story 12 | 7 | 0 | 0 | 2 | 0 | 0 | 1 | 3 | 1 | 0 | 0 | 7
Story 14 | 9 | 0 | 0 | 3 | 0 | 1 | 0 | 2 | 3 | 0 | 0 | 9
Actual Hours Remaining | 51 | 51 | 47 | 37.5 | 34.5 | 28 | 23 | 16 | 11 | 7 | 0
Estimated Hours Remaining | 58 | 52.2 | 46.4 | 40.6 | 34.8 | 29 | 23.2 | 17.4 | 11.6 | 5.8 | 0

## Sprint 2
|  | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
Story 1 | 7 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 7
Story 4 | 8.5 | 0 | 2 | 2 | 3 | 1 | 0 | 0.5 | 0 | 0 | 0 | 8.5
Story 5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1.5 | 0 | 1 | 2 | 5.5
Story 18 | 8 | 0 | 1 | 3 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 8
Actual Hours Remaining | 29 | 29 | 26 | 18 | 13 | 9 | 7 | 5 | 3 | 2 | 0
Estimated Hours Remaining | 32 | 28.8 | 25.6 | 22.4 | 19.2 | 16 | 12.8 | 9.6 | 6.4 | 3.2 | 0

## Sprint 3
Hours Spent
|  | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30
Story 19 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0.5 | 7.5 | 7
Story 20 | 5.5 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1.5 | 2 | 5.5 | 5.5
Story 16 | 3 | 0 | 2 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
Story 17 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
Story 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 4 | 4
Story 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 4 | 4
Actual Hours Remaining | 27 | 27 | 25 | 20 | 20 | 20 | 20 | 15 | 11 | 3.5 | 0
Estimated Hours Remaining | 58 | 52.2 | 46.4 | 40.6 | 34.8 | 29 | 23.2 | 17.4 | 11.6 | 5.8 | 0

## Sprint 4
Hours Spent
|  | Day 31 | Day 32 | Day 33 | Day 34 | Day 35 | Day 36 | Day 37 | Day 38 | Day 39 | Day 40
Story 6 | 10 | 0 | 0 | 0 | 0 | 4 | 0 | 6 | 0 | 0 | 0 | 10 | Sam
Story 7 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Reeve
Story 3 | 10 | 0 | 0 | 0 | 3 | 2 | 0 | 3 | 2 | 0 | 0 | 10 | Veronica
Story 21 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Hayden
Modification | 17 | 0 | 1 | 2 | 1 | 3 | 0 | 0 | 5 | 5 | 0 | 17 | Matthew
Actual Hours Remaining | 39 | 39 | 38 | 36 | 31 | 21 | 21 | 12 | 5 | 0 | 0
Estimated Hours Remaining | 58 | 52.2 | 46.4 | 40.6 | 34.8 | 29 | 23.2 | 17.4 | 11.6 | 5.8 | 0

## Assigned Stories
Story Name
| Task No | Task Description | Status | Assigned To | Estimated Hours | Time Taken | Effort Hours Remaining
14.5
Story 8 - Sprint 1 | T001 | Create a home page (customers view of website) | Closed | Matthew | 2 | 1.5 | 13
| T002 | Write test cases | Closed |  | 2 | 1 | 12
| T003 | Create login system for customers (connects to database) | Closed |  | 3 | 3 | 9
| T004 | Create profile / shipping management page | Closed |  | 2 | 1 | 8
| T005 | Create table in the database to store pickup requests | Closed |  | 0.5 | 0.5 | 7.5
| T006 | Create book shipment form | Closed |  | 1.5 | 1 | 6.5
| T007 | Write code to connect and submit to the database (pickup request table) | Closed |  | 1 | 1 | 5.5
| T008 | Create page to show all pending shipments | Closed |  | 1.5 | 1 | 4.5
| T009 | Verify story is complete (acceptance criteria test) | Closed |  | 1 | 1 | 3.5
Story 9 - Sprint 1 | T010 | Create a tracking page (customers view of website) | Closed | Veronica | 1 | 1
| T011 | Write test cases | Closed |  | 2 | 1.5
| T012 | Connecting to the database and selecting the unique tracking number. | Closed |  | 1 | 1
| T013 | Create page outputting the results of the tracking number in a visually appealing tabular format. | Closed |  | 2 | 3
| T014 | Verify story is complete (acceptance criteria test) | Closed |  | 1 | 1
Story 10 - Sprint 1 | T015 | Create the pdf template for the consignment note. | Closed | Hayden | 1.5 | 2
| T016 | Write test cases. | Closed |  | 1 | 0.5
| T017 | Connect to database and select relevant information for the consignment note. | Closed |  | 1 | 1
| T018 | Generate a printable copy of the consignment note. | Closed |  | 2 | 1
| T019 | Write code to save the consignment note to the database | Closed |  | 2 | 1
| T020 | Verify story is complete (acceptance criteria test) | Closed |  | 1 | 1
Story 11 - Sprint 1 | T021 | Create the estimate shipping webpage. | Closed | Reeve | 1 | 1
| T022 | Write test cases. | Closed |  | 1 | 1
| T023 | Write code (formula) to calculate the shipping cost based off the information given in the form. | Closed |  | 2 | 2.5
| T024 | Create page to output the results of the calculation | Closed |  | 0.5 | 0.5
| T025 | Verify story is complete (acceptance criteria test). | Closed |  | 2 | 1.5
Story 12 - Sprint 1 | T026 | Create the pdf template for the tax invoice. | Closed | Hayden | 1.5 | 2
| T027 | Write test cases. | Closed |  | 1 | 0.5
| T028 | Connect to database and select relevant information for the tax invoice. | Closed |  | 1 | 1
| T029 | Generate a printable copy of the tax invoice. | Closed |  | 2 | 0
| T030 | Write code to email a pdf copy of the invoice. | Closed |  | 2 | 2
| T031 | Write code to save the tax invoice to the database | Closed |  | 2 | 0.5
| T032 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 1
Story 14 - Sprint 1 | T033 | Create registration page (where users registers). | Closed | Samuel | 1.5 | 2
| T034 | Write test cases. | Closed |  | 2 | 1
| T035 | Write code to submit the registration information to the database | Closed |  | 2 | 1.5
| T036 | Create a personal profile page and write code to retrieve user details from the database. | Closed |  | 2 | 1
| T037 | Write code to retrieve the user information from the database and output it to the “make a booking” page. | Closed |  | 2.5 | 2.5
| T038 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 1
Story 1 - Sprint 2 | T039 | Create dashboard portal for employees | Closed | Reeve | 3 | 2
| T040 | Write test cases. | Closed |  | 2 | 0.5
| T041 | Create page within the dashboard for displaying a list of contacts. | Closed |  | 2 | 1
| T042 | Create customers table within the database to store their details. | Closed |  | 0.5 | 0.5
| T043 | Write code to connect to the database and output the results in a list. | Closed |  | 1 | 1
| T044 | Use plugin to create pagination for data | Closed |  | 1 | 0.5
| T045 | Create page within the dashboard for displaying all the data related to a single customer | Closed |  | 2 | 1.5
| T046 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 0.5
Story 4 - Sprint 2 | T047 | Create page within the dashboard for displaying a list of shipments - with pagination plugin. | Closed | Veronica | 2 | 2
| T048 | Write test cases. | Closed |  | 2 | 1
| T049 | Write code to connect to the database and output the shipment results in a list. | Closed |  | 0.5 | 0.5
| T050 | Create a page within the dashboard for displaying all the data related to a single shipment (individual shipment page) | Closed |  | 2 | 2
| T051 | Create a page within the dashboard to give the user the option to update the status. | Closed |  | 1 | 1
| T052 | Write code to modify the shipment status in the database | Closed |  | 0.5 | 1
| T053 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 1
Story 5 - Sprint 2 | T054 | Create page within the dashboard for displaying a list of payments - with pagination plugin. | Closed | Hayden | 2 | 1.5
| T055 | Write test cases. | Closed |  | 1 | 0.5
| T056 | Write code to connect to the database and output the payment results in a list. | Closed |  | 0.5 | 0.5
| T057 | Create a page within the dashboard to give the user the option to update the status of the payment. | Closed |  | 1 | 1
| T058 | Write code to modify the payment status in the database | Closed |  | 0.5 | 1
| T059 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 1
Story 18 - Sprint 2 | T060 | Create page within the dashboard for displaying a list of all pending pickups and package drop offs - with pagination plugin (table sorted by postcode). | Closed | Samuel | 2 | 0.5
| T061 | Write test cases. | Closed |  | 1 | 0.5
| T062 | Create a page to assign certain deliveries or pickups to a single driver. | Closed |  | 2 | 6
| T063 | Write code to modify the shipment data in the database to reflect the employee’s id. | Closed |  | 0.5 | 0.5
| T064 | Write code to send an automatic notification to the driver that they have been assigned pickups or deliveries. | Closed |  | 1 | 0.5
Story 19 - Sprint 3 | T065 | Write test cases. | Closed | Matthew | 1 | 1
| T066 | Create expenses page where the coordinator can view all expenses. | Closed |  | 1.5 | 1.5
| T067 | Create a table within the database which stores expenses | Closed |  | 0.5 | 0.5
| T068 | Create a php connection on the expenses page to output all of the expenses within the expenses table. | Closed |  | 0.5 | 1
| T069 | Create a page with a form where the coordinator can add expenses incurred by employees. | Closed |  | 1 | 0.5
| T070 | Create a page that submits data that is entered into the form to the database, which redirects back to the expenses page. | Closed |  | 1 | 1
| T071 | Verify story is complete (acceptance criteria test). | Closed |  | 0.5 | 0.5
Story 20 - Sprint 3 | T072 | Create page within the dashboard with forms for a pickup request. | Closed | Reeve | 2 | 2
| T073 | Create table in the database and write code to connect and store the information entered into the form. | Closed |  | 2 | 1.5
| T074 | Create page to display a list of existing requests | Closed |  | 1.5 | 1
| T075 | Write test cases. | Closed |  | 1 | 0.5
| T076 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 0.5
Story 16 - Sprint 3 | T077 | Create a page within the Coordinator Dashboard to allow the Coordinator to send notifications. | Closed | Samuel | 3 | 1.5
| T078 | Create a script capable of taking data submitted by the notification creator page and sending it to all receivers. | Closed |  | 1.5 | 1
| T079 | Write Test Cases | Closed |  | 1 | 1
| T080 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 1
Story 17 - Sprint 3 | T081 | Create a page within the Coordinator Dashboard to allow the Coordinator to send emergency notifications. | Closed | Samuel | 3 | 1.5
| T082 | Create a script capable of taking data submitted by the notification creator page and sending it to all receivers. | Closed |  | 1.5 | 1
| T083 | Write Test Cases | Closed |  | 1 | 1
| T084 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 1
| T085 |  | Closed
| T086 |  | Closed
Story 3 - Sprint 3 | T087 | Write tracking page where coordinator can track the packages | Closed | Veronica | 3 | 3
| T088 | Write test cases | Closed |  | 1 | 1
| T089 | Include the pages in the sidebar | Closed |  | 0.5 | 0.5
| T090 | Write the driver journey page where the driver can notify the start and end time of their journey | Closed |  | 3 | 4
| T091 | Create the buttons for start and end time | Closed |  | 0.5 | 1
| T092 | Create a table within the database for the start and end button of the driver's journey | Closed |  | 1 | 1
| T093 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 1
| T094 |  | Closed
| T095 |  | Closed
Story 6 - Daily Summary of Deliveryies | T096 | Create a page where drivers are able to view all deliveries filtered by day and ordered by delivery time. | Closed |  | 4 | 3
| T097 | Modify the database to store the additional data needed for this page. | Closed |  | 0.5 | 1
| T098 | Incorporate page into driver dashboard. | Closed |  | 0.5 | 0.5
| T099 | Write test cases. | Closed |  | 0.5 | 0.5
| T100 | Verify story is complete (acceptance criteria test). | Closed |  | 0.5 | 0.5
Story 7 - See Individual Delivery Details | T101 | Create an overview page to view a list of deliveries | Closed |  | 0.5 | 0.5
| T102 | Write test cases. | Closed |  | 0.5 | 0.5
| T103 | Create a link to the database that retrieves the assigned deliveries. | Closed |  | 0.5 | 0.5
| T104 | Create a table to outputs the retrieved data. | Closed |  | 1 | 1
| T105 | Verify story is complete (acceptance criteria test). | Closed |  | 0.5 | 0.5
| T106 | Refine the work done on the contacts list and page done in sprint 2. | Closed |  | 1 | 1
| T107 | Finish the manual bookings page for the coordinator in sprint 3 | Closed |  | 2 | 1.5
Story 22 - Accessing Tracking Details | T108 | Add a table module on the dashboard to display saved tracking number. | Closed |  | 0.5 | 0.5
| T109 | Create a connection to the database that pulls saved tracking numbers | Closed |  | 0.5 | 0.5
| T110 | Write code to output the retrieved tracking numbers. | Closed |  | 1 | 0.5
| T111 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 1
Story 23 - Scanning Connote Numbers and Modifying Shipment Status | T112 | Creating page within the driver dashboard that the driver can type in the connote number and get results back. | Closed |  | 1 | 1
| T113 | Write test cases. | Closed |  | 1 | 1
| T114 | Create a link to the database that retrieves all details about the package based off the connote number. | Closed |  | 1 | 1
| T115 | Implement a way for the driver to update the packages status in the database. | Closed |  | 2 | 1.5
| T116 | Verify story is complete (acceptance criteria test). | Closed |  | 0.5 | 0.5