## Sprint 1
Hours Spent
|  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Story 8 | 14.5 | 0 | 2 | 4 | 0 | 2.5 | 0 | 2 | 1 | 0 | 3 | 14.5
Story 9 | 7.5 | 0 | 0 | 0.5 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 7.5
Story 10 | 6.5 | 0 | 2 | 0 | 3 | 0 | 1.5 | 0 | 0 | 0 | 0 | 6.5
Story 11 | 6.5 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 2 | 2 | 6.5
Story 12 | 7 | 0 | 0 | 2 | 0 | 0 | 1 | 3 | 1 | 0 | 0 | 7
Story 14 | 9 | 0 | 0 | 3 | 0 | 1 | 0 | 2 | 3 | 0 | 0 | 9
Actual Hours Remaining | 51 | 51 | 47 | 37.5 | 34.5 | 28 | 23 | 16 | 11 | 7 | 0
Estimated Hours Remaining | 58 | 52.2 | 46.4 | 40.6 | 34.8 | 29 | 23.2 | 17.4 | 11.6 | 5.8 | 0

## Sprint 2
|  | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
Story 1 | 7 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 7
Story 4 | 8.5 | 0 | 2 | 2 | 3 | 1 | 0 | 0.5 | 0 | 0 | 0 | 8.5
Story 5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1.5 | 0 | 1 | 2 | 5.5
Story 18 | 8 | 0 | 1 | 3 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 8
Actual Hours Remaining | 29 | 29 | 26 | 18 | 13 | 9 | 7 | 5 | 3 | 2 | 0
Estimated Hours Remaining | 32 | 28.8 | 25.6 | 22.4 | 19.2 | 16 | 12.8 | 9.6 | 6.4 | 3.2 | 0

## Sprint 3
Hours Spent
|  | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30
Story 19 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0.5 | 7.5 | 7
Story 20 | 5.5 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1.5 | 2 | 5.5 | 5.5
Story 16 | 3 | 0 | 2 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
Story 17 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
Story 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 4 | 4
Story 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 4 | 4
Actual Hours Remaining | 27 | 27 | 25 | 20 | 20 | 20 | 20 | 15 | 11 | 3.5 | 0
Estimated Hours Remaining | 58 | 52.2 | 46.4 | 40.6 | 34.8 | 29 | 23.2 | 17.4 | 11.6 | 5.8 | 0

## Sprint 4
Hours Spent
|  | Day 31 | Day 32 | Day 33 | Day 34 | Day 35 | Day 36 | Day 37 | Day 38 | Day 39 | Day 40
Story 6 | 5.5 | 0 | 0 | 0 | 0 | 4 | 0 | 1.5 | 0 | 0 | 0 | 5.5
Story 7 | 5.5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1.5 | 0 | 5.5
Story 3 | 10 | 0 | 0 | 0 | 3 | 2 | 0 | 3 | 2 | 0 | 0 | 10
Story 21 | 4 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 4
Story 22 | 2.5 | 0 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5
Story 23 | 5 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Actual Hours Remaining | 32.5 | 32.5 | 30.5 | 28 | 22 | 12 | 11 | 6.5 | 1.5 | 0 | 0
Estimated Hours Remaining | 58 | 52.2 | 46.4 | 40.6 | 34.8 | 29 | 23.2 | 17.4 | 11.6 | 5.8 | 0

## Release 1
[5 empty] | 92 | 92 | 77 | 77
Story 8 - Sprint 1 | T001 | Create a home page (customers view of website) | Closed | Matthew | 2 | 90 | 1.5 | 75.5 | 65
| T002 | Write test cases | Closed |  | 2 | 88 | 1 | 74.5 | 64
| T003 | Create login system for customers (connects to database) | Closed |  | 3 | 85 | 3 | 71.5 | 63
| T004 | Create profile / shipping management page | Closed |  | 2 | 83 | 1 | 70.5 | 62
| T005 | Create table in the database to store pickup requests | Closed |  | 0.5 | 82.5 | 0.5 | 70 | 61
| T006 | Create book shipment form | Closed |  | 1.5 | 81 | 1 | 69 | 60
| T007 | Write code to connect and submit to the database (pickup request table) | Closed |  | 1 | 80 | 1 | 68 | 59
| T008 | Create page to show all pending shipments | Closed |  | 1.5 | 78.5 | 1 | 67 | 58
| T009 | Verify story is complete (acceptance criteria test) | Closed |  | 1 | 77.5 | 1 | 66 | 57
Story 9 - Sprint 1 | T010 | Create a tracking page (customers view of website) | Closed | Veronica | 1 | 76.5 | 1 | 65 | 56
| T011 | Write test cases | Closed |  | 2 | 74.5 | 1.5 | 63.5 | 55
| T012 | Connecting to the database and selecting the unique tracking number. | Closed |  | 1 | 73.5 | 1 | 62.5 | 54
| T013 | Create page outputting the results of the tracking number in a visually appealing tabular format. | Closed |  | 2 | 71.5 | 3 | 59.5 | 53
| T014 | Verify story is complete (acceptance criteria test) | Closed |  | 1 | 70.5 | 1 | 58.5 | 52
Story 10 - Sprint 1 | T015 | Create the pdf template for the consignment note. | Closed | Hayden | 1.5 | 69 | 2 | 56.5 | 51
| T016 | Write test cases. | Closed |  | 1 | 68 | 0.5 | 56 | 50
| T017 | Connect to database and select relevant information for the consignment note. | Closed |  | 1 | 67 | 1 | 55 | 49
| T018 | Generate a printable copy of the consignment note. | Closed |  | 2 | 65 | 1 | 54 | 48
| T019 | Write code to save the consignment note to the database | Closed |  | 2 | 63 | 1 | 53 | 47
| T020 | Verify story is complete (acceptance criteria test) | Closed |  | 1 | 62 | 1 | 52 | 46
Story 11 - Sprint 1 | T021 | Create the estimate shipping webpage. | Closed | Reeve | 1 | 61 | 1 | 51 | 45
| T022 | Write test cases. | Closed |  | 1 | 60 | 1 | 50 | 44
| T023 | Write code (formula) to calculate the shipping cost based off the information given in the form. | Closed |  | 2 | 58 | 2.5 | 47.5 | 43
| T024 | Create page to output the results of the calculation | Closed |  | 0.5 | 57.5 | 0.5 | 47 | 42
| T025 | Verify story is complete (acceptance criteria test). | Closed |  | 2 | 55.5 | 1.5 | 45.5 | 41
Story 12 - Sprint 1 | T026 | Create the pdf template for the tax invoice. | Closed | Hayden | 1.5 | 54 | 2 | 43.5 | 40
| T027 | Write test cases. | Closed |  | 1 | 53 | 0.5 | 43 | 39
| T028 | Connect to database and select relevant information for the tax invoice. | Closed |  | 1 | 52 | 1 | 42 | 38
| T029 | Generate a printable copy of the tax invoice. | Closed |  | 2 | 50 | 0 | 42 | 37
| T030 | Write code to email a pdf copy of the invoice. | Closed |  | 2 | 48 | 2 | 40 | 36
| T031 | Write code to save the tax invoice to the database | Closed |  | 2 | 46 | 0.5 | 39.5 | 35
| T032 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 45 | 1 | 38.5 | 34
Story 14 - Sprint 1 | T033 | Create registration page (where users registers). | Closed | Samuel | 1.5 | 43.5 | 2 | 36.5 | 33
| T034 | Write test cases. | Closed |  | 2 | 41.5 | 1 | 35.5 | 32
| T035 | Write code to submit the registration information to the database | Closed |  | 2 | 39.5 | 1.5 | 34 | 31
| T036 | Create a personal profile page and write code to retrieve user details from the database. | Closed |  | 2 | 37.5 | 1 | 33 | 30
| T037 | Write code to retrieve the user information from the database and output it to the “make a booking” page. | Closed |  | 2.5 | 35 | 2.5 | 30.5 | 29
| T038 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 34 | 1 | 29.5 | 28
Story 1 - Sprint 2 | T039 | Create dashboard portal for employees | Closed | Reeve | 3 | 31 | 2 | 27.5 | 27
| T040 | Write test cases. | Closed |  | 2 | 29 | 0.5 | 27 | 26
| T041 | Create page within the dashboard for displaying a list of contacts. | Closed |  | 2 | 27 | 1 | 26 | 25
| T042 | Create customers table within the database to store their details. | Closed |  | 0.5 | 26.5 | 0.5 | 25.5 | 24
| T043 | Write code to connect to the database and output the results in a list. | Closed |  | 1 | 25.5 | 1 | 24.5 | 23
| T044 | Use plugin to create pagination for data | Closed |  | 1 | 24.5 | 0.5 | 24 | 22
| T045 | Create page within the dashboard for displaying all the data related to a single customer | Closed |  | 2 | 22.5 | 1.5 | 22.5 | 21
| T046 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 21.5 | 0.5 | 22 | 20
Story 4 - Sprint 2 | T047 | Create page within the dashboard for displaying a list of shipments - with pagination plugin. | Closed | Veronica | 2 | 19.5 | 2 | 20 | 19
| T048 | Write test cases. | Closed |  | 2 | 17.5 | 1 | 19 | 18
| T049 | Write code to connect to the database and output the shipment results in a list. | Closed |  | 0.5 | 17 | 0.5 | 18.5 | 17
| T050 | Create a page within the dashboard for displaying all the data related to a single shipment (individual shipment page) | Closed |  | 2 | 15 | 2 | 16.5 | 16
| T051 | Create a page within the dashboard to give the user the option to update the status. | Closed |  | 1 | 14 | 1 | 15.5 | 15
| T052 | Write code to modify the shipment status in the database | Closed |  | 0.5 | 13.5 | 1 | 14.5 | 14
| T053 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 12.5 | 1 | 13.5 | 13
Story 5 - Sprint 2 | T054 | Create page within the dashboard for displaying a list of payments - with pagination plugin. | Closed | Hayden | 2 | 10.5 | 1.5 | 12 | 12
| T055 | Write test cases. | Closed |  | 1 | 9.5 | 0.5 | 11.5 | 11
| T056 | Write code to connect to the database and output the payment results in a list. | Closed |  | 0.5 | 9 | 0.5 | 11 | 10
| T057 | Create a page within the dashboard to give the user the option to update the status of the payment. | Closed |  | 1 | 8 | 1 | 10 | 9
| T058 | Write code to modify the payment status in the database | Closed |  | 0.5 | 7.5 | 1 | 9 | 8
| T059 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 6.5 | 1 | 8 | 7
Story 18 - Sprint 2 | T060 | Create page within the dashboard for displaying a list of all pending pickups and package drop offs - with pagination plugin (table sorted by postcode). | Closed | Samuel | 2 | 4.5 | 0.5 | 7.5 | 6
| T061 | Write test cases. | Closed |  | 1 | 3.5 | 0.5 | 7 | 5
| T062 | Create a page to assign certain deliveries or pickups to a single driver. | Closed |  | 2 | 1.5 | 6 | 1 | 4
| T063 | Write code to modify the shipment data in the database to reflect the employee’s id. | Closed |  | 0.5 | 1 | 0.5 | 0.5 | 3
| T064 | Write code to send an automatic notification to the driver that they have been assigned pickups or deliveries. | Closed |  | 1 | 0 | 0.5 | 0 | 2
1
0

## Release 2
[5 empty] | 61 | 61 | 54.5 | 54.5
Story 19 - Sprint 3 | T065 | Write test cases. | Closed | Matthew | 1 | 60 | 1 | 53.5 | 53
| T066 | Create expenses page where the coordinator can view all expenses. | Closed |  | 1.5 | 58.5 | 1.5 | 52 | 52
| T067 | Create a table within the database which stores expenses | Closed |  | 0.5 | 58 | 0.5 | 51.5 | 51
| T068 | Create a php connection on the expenses page to output all of the expenses within the expenses table. | Closed |  | 0.5 | 57.5 | 1 | 50.5 | 50
| T069 | Create a page with a form where the coordinator can add expenses incurred by employees. | Closed |  | 1 | 56.5 | 0.5 | 50 | 49
| T070 | Create a page that submits data that is entered into the form to the database, which redirects back to the expenses page. | Closed |  | 1 | 55.5 | 1 | 49 | 48
| T071 | Verify story is complete (acceptance criteria test). | Closed |  | 0.5 | 55 | 0.5 | 48.5 | 47
Story 20 - Sprint 3 | T072 | Create page within the dashboard with forms for a pickup request. | Closed | Reeve | 2 | 53 | 2 | 46.5 | 46
| T073 | Create table in the database and write code to connect and store the information entered into the form. | Closed |  | 2 | 51 | 1.5 | 45 | 45
| T074 | Create page to display a list of existing requests | Closed |  | 1.5 | 49.5 | 1 | 44 | 44
| T075 | Write test cases. | Closed |  | 1 | 48.5 | 0.5 | 43.5 | 43
| T076 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 47.5 | 0.5 | 43 | 42
Story 16 - Sprint 3 | T077 | Create a page within the Coordinator Dashboard to allow the Coordinator to send notifications. | Closed | Samuel | 3 | 44.5 | 1.5 | 41.5 | 41
| T078 | Create a script capable of taking data submitted by the notification creator page and sending it to all receivers. | Closed |  | 1.5 | 43 | 1 | 40.5 | 40
| T079 | Write Test Cases | Closed |  | 1 | 42 | 1 | 39.5 | 39
| T080 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 41 | 1 | 38.5 | 38
Story 17 - Sprint 3 | T081 | Create a page within the Coordinator Dashboard to allow the Coordinator to send emergency notifications. | Closed | Samuel | 3 | 38 | 1.5 | 37 | 37
| T082 | Create a script capable of taking data submitted by the notification creator page and sending it to all receivers. | Closed |  | 1.5 | 36.5 | 1 | 36 | 36
| T083 | Write Test Cases | Closed |  | 1 | 35.5 | 1 | 35 | 35
| T084 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 34.5 | 1 | 34 | 34
Story 3 - Sprint 3 | T085 | Write tracking page where coordinator can track the packages | Closed | Veronica | 3 | 31.5 | 3 | 31 | 33
| T086 | Write test cases | Closed |  | 1 | 30.5 | 1 | 30 | 32
| T087 | Include the pages in the sidebar | Closed |  | 0.5 | 30 | 0.5 | 29.5 | 31
| T088 | Write the driver journey page where the driver can notify the start and end time of their journey | Closed |  | 3 | 27 | 4 | 25.5 | 30
| T089 | Create the buttons for start and end time | Closed |  | 0.5 | 26.5 | 1 | 24.5 | 29
| T090 | Create a table within the database for the start and end button of the driver's journey | Closed |  | 1 | 25.5 | 1 | 23.5 | 28
| T091 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 24.5 | 1 | 22.5 | 27
Story 21 - Sprint 4 | T092 | Create a page for drivers to check what shift they are rostered on for the following two weeks | Closed | Hayden | 1 | 23.5 | 1 | 21.5 | 26
| T093 | Have driver page autofill based on login credentials | Closed |  |  | 23.5 |  | 21.5 | 25
| T094 | Create a page for the coordinator to view the shifts for all of the employees | Closed |  | 1 | 22.5 | 0.5 | 21 | 24
| T095 | Allow the coordinator to change the shifts of the drivers. | Closed |  | 2 | 20.5 | 2.5 | 18.5 | 23
Story 6 - Sprint 4 | T096 | Create a page where drivers are able to view all deliveries filtered by day and ordered by delivery time. | Closed | Samuel | 4 | 16.5 | 3 | 15.5 | 22
| T097 | Modify the database to store the additional data needed for this page. | Closed |  | 0.5 | 16 | 1 | 14.5 | 21
| T098 | Incorporate page into driver dashboard. | Closed |  | 0.5 | 15.5 | 0.5 | 14 | 20
| T099 | Write test cases. | Closed |  | 0.5 | 15 | 0.5 | 13.5 | 19
| T100 | Verify story is complete (acceptance criteria test). | Closed |  | 0.5 | 14.5 | 0.5 | 13 | 18
Story 7 -Sprint 4 | T101 | Create an overview page to view a list of deliveries | Closed | Reeve | 0.5 | 14 | 0.5 | 12.5 | 17
| T102 | Write test cases. | Closed |  | 0.5 | 13.5 | 0.5 | 12 | 16
| T103 | Create a link to the database that retrieves the assigned deliveries. | Closed |  | 0.5 | 13 | 0.5 | 11.5 | 15
| T104 | Create a table to outputs the retrieved data. | Closed |  | 1 | 12 | 1 | 10.5 | 14
| T105 | Verify story is complete (acceptance criteria test). | Closed |  | 0.5 | 11.5 | 0.5 | 10 | 13
| T106 | Refine the work done on the contacts list and page done in sprint 2. | Closed |  | 1 | 10.5 | 1 | 9 | 12
| T107 | Finish the manual bookings page for the coordinator in sprint 3 | Closed |  | 2 | 8.5 | 1.5 | 7.5 | 11
Story 22 - Sprint 4 | T108 | Add a table module on the dashboard to display saved tracking number. | Closed | Matthew | 0.5 | 8 | 0.5 | 7 | 10
| T109 | Create a connection to the database that pulls saved tracking numbers | Closed |  | 0.5 | 7.5 | 0.5 | 6.5 | 9
| T110 | Write code to output the retrieved tracking numbers. | Closed |  | 1 | 6.5 | 0.5 | 6 | 8
| T111 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 5.5 | 1 | 5 | 7
Story 23 - Sprint 4 | T112 | Creating page within the driver dashboard that the driver can type in the connote number and get results back. | Closed | Matthew | 1 | 4.5 | 1 | 4 | 6
| T113 | Write test cases. | Closed |  | 1 | 3.5 | 1 | 3 | 5
| T114 | Create a link to the database that retrieves all details about the package based off the connote number. | Closed |  | 1 | 2.5 | 1 | 2 | 4
| T115 | Implement a way for the driver to update the packages status in the database. | Closed |  | 2 | 0.5 | 1.5 | 0.5 | 3
| T116 | Verify story is complete (acceptance criteria test). | Closed |  | 0.5 | 0 | 0.5 | 0 | 2
1
0

## Assigned Stories
Story Name | Task No | Task Description | Status | Assigned To | Estimated Hours | Estimated Hours Remaining | Time Taken | Effort Hours Remaining
[5 empty] | 153 | 153 | 131.5 | 131.5
Story 8 - Sprint 1 | T001 | Create a home page (customers view of website) | Closed | Matthew | 2 | 151 | 1.5 | 130 | T116
| T002 | Write test cases | Closed |  | 2 | 149 | 1 | 129 | T115
| T003 | Create login system for customers (connects to database) | Closed |  | 3 | 146 | 3 | 126 | T114
| T004 | Create profile / shipping management page | Closed |  | 2 | 144 | 1 | 125 | T113
| T005 | Create table in the database to store pickup requests | Closed |  | 0.5 | 143.5 | 0.5 | 124.5 | T112
| T006 | Create book shipment form | Closed |  | 1.5 | 142 | 1 | 123.5 | T111
| T007 | Write code to connect and submit to the database (pickup request table) | Closed |  | 1 | 141 | 1 | 122.5 | T110
| T008 | Create page to show all pending shipments | Closed |  | 1.5 | 139.5 | 1 | 121.5 | T109
| T009 | Verify story is complete (acceptance criteria test) | Closed |  | 1 | 138.5 | 1 | 120.5 | T108
Story 9 - Sprint 1 | T010 | Create a tracking page (customers view of website) | Closed | Veronica | 1 | 137.5 | 1 | 119.5 | T107
| T011 | Write test cases | Closed |  | 2 | 135.5 | 1.5 | 118 | T106
| T012 | Connecting to the database and selecting the unique tracking number. | Closed |  | 1 | 134.5 | 1 | 117 | T105
| T013 | Create page outputting the results of the tracking number in a visually appealing tabular format. | Closed |  | 2 | 132.5 | 3 | 114 | T104
| T014 | Verify story is complete (acceptance criteria test) | Closed |  | 1 | 131.5 | 1 | 113 | T103
Story 10 - Sprint 1 | T015 | Create the pdf template for the consignment note. | Closed | Hayden | 1.5 | 130 | 2 | 111 | T102
| T016 | Write test cases. | Closed |  | 1 | 129 | 0.5 | 110.5 | T101
| T017 | Connect to database and select relevant information for the consignment note. | Closed |  | 1 | 128 | 1 | 109.5 | T100
| T018 | Generate a printable copy of the consignment note. | Closed |  | 2 | 126 | 1 | 108.5 | T99
| T019 | Write code to save the consignment note to the database | Closed |  | 2 | 124 | 1 | 107.5 | T98
| T020 | Verify story is complete (acceptance criteria test) | Closed |  | 1 | 123 | 1 | 106.5 | T97
Story 11 - Sprint 1 | T021 | Create the estimate shipping webpage. | Closed | Reeve | 1 | 122 | 1 | 105.5 | T96
| T022 | Write test cases. | Closed |  | 1 | 121 | 1 | 104.5 | T95
| T023 | Write code (formula) to calculate the shipping cost based off the information given in the form. | Closed |  | 2 | 119 | 2.5 | 102 | T94
| T024 | Create page to output the results of the calculation | Closed |  | 0.5 | 118.5 | 0.5 | 101.5 | T93
| T025 | Verify story is complete (acceptance criteria test). | Closed |  | 2 | 116.5 | 1.5 | 100 | T92
Story 12 - Sprint 1 | T026 | Create the pdf template for the tax invoice. | Closed | Hayden | 1.5 | 115 | 2 | 98 | T91
| T027 | Write test cases. | Closed |  | 1 | 114 | 0.5 | 97.5 | T90
| T028 | Connect to database and select relevant information for the tax invoice. | Closed |  | 1 | 113 | 1 | 96.5 | T89
| T029 | Generate a printable copy of the tax invoice. | Closed |  | 2 | 111 | 0 | 96.5 | T88
| T030 | Write code to email a pdf copy of the invoice. | Closed |  | 2 | 109 | 2 | 94.5 | T87
| T031 | Write code to save the tax invoice to the database | Closed |  | 2 | 107 | 0.5 | 94 | T86
| T032 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 106 | 1 | 93 | T85
Story 14 - Sprint 1 | T033 | Create registration page (where users registers). | Closed | Samuel | 1.5 | 104.5 | 2 | 91 | T84
| T034 | Write test cases. | Closed |  | 2 | 102.5 | 1 | 90 | T83
| T035 | Write code to submit the registration information to the database | Closed |  | 2 | 100.5 | 1.5 | 88.5 | T82
| T036 | Create a personal profile page and write code to retrieve user details from the database. | Closed |  | 2 | 98.5 | 1 | 87.5 | T81
| T037 | Write code to retrieve the user information from the database and output it to the “make a booking” page. | Closed |  | 2.5 | 96 | 2.5 | 85 | T80
| T038 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 95 | 1 | 84 | T79
Story 1 - Sprint 2 | T039 | Create dashboard portal for employees | Closed | Reeve | 3 | 92 | 2 | 82 | T78
| T040 | Write test cases. | Closed |  | 2 | 90 | 0.5 | 81.5 | T77
| T041 | Create page within the dashboard for displaying a list of contacts. | Closed |  | 2 | 88 | 1 | 80.5 | T76
| T042 | Create customers table within the database to store their details. | Closed |  | 0.5 | 87.5 | 0.5 | 80 | T75
| T043 | Write code to connect to the database and output the results in a list. | Closed |  | 1 | 86.5 | 1 | 79 | T74
| T044 | Use plugin to create pagination for data | Closed |  | 1 | 85.5 | 0.5 | 78.5 | T73
| T045 | Create page within the dashboard for displaying all the data related to a single customer | Closed |  | 2 | 83.5 | 1.5 | 77 | T72
| T046 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 82.5 | 0.5 | 76.5 | T71
Story 4 - Sprint 2 | T047 | Create page within the dashboard for displaying a list of shipments - with pagination plugin. | Closed | Veronica | 2 | 80.5 | 2 | 74.5 | T70
| T048 | Write test cases. | Closed |  | 2 | 78.5 | 1 | 73.5 | T69
| T049 | Write code to connect to the database and output the shipment results in a list. | Closed |  | 0.5 | 78 | 0.5 | 73 | T68
| T050 | Create a page within the dashboard for displaying all the data related to a single shipment (individual shipment page) | Closed |  | 2 | 76 | 2 | 71 | T67
| T051 | Create a page within the dashboard to give the user the option to update the status. | Closed |  | 1 | 75 | 1 | 70 | T66
| T052 | Write code to modify the shipment status in the database | Closed |  | 0.5 | 74.5 | 1 | 69 | T65
| T053 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 73.5 | 1 | 68 | T64
Story 5 - Sprint 2 | T054 | Create page within the dashboard for displaying a list of payments - with pagination plugin. | Closed | Hayden | 2 | 71.5 | 1.5 | 66.5 | T63
| T055 | Write test cases. | Closed |  | 1 | 70.5 | 0.5 | 66 | T62
| T056 | Write code to connect to the database and output the payment results in a list. | Closed |  | 0.5 | 70 | 0.5 | 65.5 | T61
| T057 | Create a page within the dashboard to give the user the option to update the status of the payment. | Closed |  | 1 | 69 | 1 | 64.5 | T60
| T058 | Write code to modify the payment status in the database | Closed |  | 0.5 | 68.5 | 1 | 63.5 | T59
| T059 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 67.5 | 1 | 62.5 | T58
Story 18 - Sprint 2 | T060 | Create page within the dashboard for displaying a list of all pending pickups and package drop offs - with pagination plugin (table sorted by postcode). | Closed | Samuel | 2 | 65.5 | 0.5 | 62 | T57
| T061 | Write test cases. | Closed |  | 1 | 64.5 | 0.5 | 61.5 | T56
| T062 | Create a page to assign certain deliveries or pickups to a single driver. | Closed |  | 2 | 62.5 | 6 | 55.5 | T55
| T063 | Write code to modify the shipment data in the database to reflect the employee’s id. | Closed |  | 0.5 | 62 | 0.5 | 55 | T54
| T064 | Write code to send an automatic notification to the driver that they have been assigned pickups or deliveries. | Closed |  | 1 | 61 | 0.5 | 54.5 | T53
Story 19 - Sprint 3 | T065 | Write test cases. | Closed | Matthew | 1 | 60 | 1 | 53.5 | T52
| T066 | Create expenses page where the coordinator can view all expenses. | Closed |  | 1.5 | 58.5 | 1.5 | 52 | T51
| T067 | Create a table within the database which stores expenses | Closed |  | 0.5 | 58 | 0.5 | 51.5 | T50
| T068 | Create a php connection on the expenses page to output all of the expenses within the expenses table. | Closed |  | 0.5 | 57.5 | 1 | 50.5 | T49
| T069 | Create a page with a form where the coordinator can add expenses incurred by employees. | Closed |  | 1 | 56.5 | 0.5 | 50 | T48
| T070 | Create a page that submits data that is entered into the form to the database, which redirects back to the expenses page. | Closed |  | 1 | 55.5 | 1 | 49 | T47
| T071 | Verify story is complete (acceptance criteria test). | Closed |  | 0.5 | 55 | 0.5 | 48.5 | T46
Story 20 - Sprint 3 | T072 | Create page within the dashboard with forms for a pickup request. | Closed | Reeve | 2 | 53 | 2 | 46.5 | T45
| T073 | Create table in the database and write code to connect and store the information entered into the form. | Closed |  | 2 | 51 | 1.5 | 45 | T44
| T074 | Create page to display a list of existing requests | Closed |  | 1.5 | 49.5 | 1 | 44 | T43
| T075 | Write test cases. | Closed |  | 1 | 48.5 | 0.5 | 43.5 | T42
| T076 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 47.5 | 0.5 | 43 | T41
Story 16 - Sprint 3 | T077 | Create a page within the Coordinator Dashboard to allow the Coordinator to send notifications. | Closed | Samuel | 3 | 44.5 | 1.5 | 41.5 | T40
| T078 | Create a script capable of taking data submitted by the notification creator page and sending it to all receivers. | Closed |  | 1.5 | 43 | 1 | 40.5 | T39
| T079 | Write Test Cases | Closed |  | 1 | 42 | 1 | 39.5 | T38
| T080 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 41 | 1 | 38.5 | T37
Story 17 - Sprint 3 | T081 | Create a page within the Coordinator Dashboard to allow the Coordinator to send emergency notifications. | Closed | Samuel | 3 | 38 | 1.5 | 37 | T36
| T082 | Create a script capable of taking data submitted by the notification creator page and sending it to all receivers. | Closed |  | 1.5 | 36.5 | 1 | 36 | T35
| T083 | Write Test Cases | Closed |  | 1 | 35.5 | 1 | 35 | T34
| T084 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 34.5 | 1 | 34 | T33
Story 3 - Sprint 3 | T085 | Write tracking page where coordinator can track the packages | Closed | Veronica | 3 | 31.5 | 3 | 31 | T32
| T086 | Write test cases | Closed |  | 1 | 30.5 | 1 | 30 | T31
| T087 | Include the pages in the sidebar | Closed |  | 0.5 | 30 | 0.5 | 29.5 | T30
| T088 | Write the driver journey page where the driver can notify the start and end time of their journey | Closed |  | 3 | 27 | 4 | 25.5 | T29
| T089 | Create the buttons for start and end time | Closed |  | 0.5 | 26.5 | 1 | 24.5 | T28
| T090 | Create a table within the database for the start and end button of the driver's journey | Closed |  | 1 | 25.5 | 1 | 23.5 | T27
| T091 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 24.5 | 1 | 22.5 | T26
Story 21 - Sprint 4 | T092 | Create a page for drivers to check what shift they are rostered on for the following two weeks | Closed | Hayden | 1 | 23.5 | 1 | 21.5 | T25
| T093 | Have driver page autofill based on login credentials | Closed |  |  | 23.5 |  | 21.5 | T24
| T094 | Create a page for the coordinator to view the shifts for all of the employees | Closed |  | 1 | 22.5 | 0.5 | 21 | T23
| T095 | Allow the coordinator to change the shifts of the drivers. | Closed |  | 2 | 20.5 | 2.5 | 18.5 | T22
Story 6 - Sprint 4 | T096 | Create a page where drivers are able to view all deliveries filtered by day and ordered by delivery time. | Closed | Samuel | 4 | 16.5 | 3 | 15.5 | T21
| T097 | Modify the database to store the additional data needed for this page. | Closed |  | 0.5 | 16 | 1 | 14.5 | T20
| T098 | Incorporate page into driver dashboard. | Closed |  | 0.5 | 15.5 | 0.5 | 14 | T19
| T099 | Write test cases. | Closed |  | 0.5 | 15 | 0.5 | 13.5 | T18
| T100 | Verify story is complete (acceptance criteria test). | Closed |  | 0.5 | 14.5 | 0.5 | 13 | T17
Story 7 -Sprint 4 | T101 | Create an overview page to view a list of deliveries | Closed | Reeve | 0.5 | 14 | 0.5 | 12.5 | T16
| T102 | Write test cases. | Closed |  | 0.5 | 13.5 | 0.5 | 12 | T15
| T103 | Create a link to the database that retrieves the assigned deliveries. | Closed |  | 0.5 | 13 | 0.5 | 11.5 | T14
| T104 | Create a table to outputs the retrieved data. | Closed |  | 1 | 12 | 1 | 10.5 | T13
| T105 | Verify story is complete (acceptance criteria test). | Closed |  | 0.5 | 11.5 | 0.5 | 10 | T12
| T106 | Refine the work done on the contacts list and page done in sprint 2. | Closed |  | 1 | 10.5 | 1 | 9 | T11
| T107 | Finish the manual bookings page for the coordinator in sprint 3 | Closed |  | 2 | 8.5 | 1.5 | 7.5 | T10
Story 22 - Sprint 4 | T108 | Add a table module on the dashboard to display saved tracking number. | Closed | Matthew | 0.5 | 8 | 0.5 | 7 | T9
| T109 | Create a connection to the database that pulls saved tracking numbers | Closed |  | 0.5 | 7.5 | 0.5 | 6.5 | T8
| T110 | Write code to output the retrieved tracking numbers. | Closed |  | 1 | 6.5 | 0.5 | 6 | T7
| T111 | Verify story is complete (acceptance criteria test). | Closed |  | 1 | 5.5 | 1 | 5 | T6
Story 23 - Sprint 4 | T112 | Creating page within the driver dashboard that the driver can type in the connote number and get results back. | Closed | Matthew | 1 | 4.5 | 1 | 4 | T5
| T113 | Write test cases. | Closed |  | 1 | 3.5 | 1 | 3 | T4
| T114 | Create a link to the database that retrieves all details about the package based off the connote number. | Closed |  | 1 | 2.5 | 1 | 2 | T3
| T115 | Implement a way for the driver to update the packages status in the database. | Closed |  | 2 | 0.5 | 1.5 | 0.5 | T2
| T116 | Verify story is complete (acceptance criteria test). | Closed |  | 0.5 | 0 | 0.5 | 0 | T1