## Sprint 1
Hours Spent
|  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Story 8 | 14.5 | 0 | 2 | 4 | 0 | 2.5 | 0 | 2 | 1 | 0 | 3 | 14.5
Story 9 | 7.5 | 0 | 0 | 0.5 | 0 | 3 | 0 | 0 | 0 | 2 | 2 | 7.5
Story 10 | 6.5 | 0 | 2 | 0 | 3 | 0 | 1.5 | 0 | 0 | 0 | 0 | 6.5
Story 11 | 6.5 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 2 | 2 | 6.5
Story 12 | 7 | 0 | 0 | 2 | 0 | 0 | 1 | 3 | 1 | 0 | 0 | 7
Story 14 | 9 | 0 | 0 | 3 | 0 | 1 | 0 | 2 | 3 | 0 | 0 | 9
Actual Hours Remaining | 51 | 51 | 47 | 37.5 | 34.5 | 28 | 23 | 16 | 11 | 7 | 0
Estimated Hours Remaining | 58 | 52.2 | 46.4 | 40.6 | 34.8 | 29 | 23.2 | 17.4 | 11.6 | 5.8 | 0

## Sprint 2
|  | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
Story 1 | 7 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 1 | 0 | 0 | 7
Story 4 | 8.5 | 0 | 2 | 2 | 3 | 1 | 0 | 0.5 | 0 | 0 | 0 | 8.5
Story 5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 1 | 1.5 | 0 | 1 | 2 | 5.5
Story 18 | 8 | 0 | 1 | 3 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 8
Actual Hours Remaining | 29 | 29 | 26 | 18 | 13 | 9 | 7 | 5 | 3 | 2 | 0
Estimated Hours Remaining | 32 | 28.8 | 25.6 | 22.4 | 19.2 | 16 | 12.8 | 9.6 | 6.4 | 3.2 | 0

## BD Story Point
| SP | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Day 32 | Day 33 | Day 34 | Day 35 | Day 36 | Day 37 | Day 38 | Day 39 | Day 40
Story 8 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 9 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 10 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 11 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 12 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 14 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 2 | 0 | 0 | 3 | 2 | 2 | 0 | 3 | 0 | 0 | 2.5 | 0 | 1 | 0 | 2.5 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 20 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 16 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 17 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Story 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Story 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
Story 22 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Story 23 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 2 | 4 | 0 | 0 | 3 | 1 | 1 | 0 | 3 | 1 | 0 | 0
| 21 | 21 | 21 | 19 | 19 | 19 | 16 | 14 | 12 | 12 | 9 | 9 | 9 | 6.5 | 6.5 | 5.5 | 5.5 | 3 | 1 | 1 | 0 | 23 | 23 | 19 | 19 | 19 | 19 | 16 | 16 | 14 | 10 | 10 | 10 | 7 | 6 | 5 | 5 | 2 | 1 | 1 | 0
Story Points Remaining | 21 | 19.95 | 18.9 | 17.85 | 16.8 | 15.75 | 14.7 | 13.65 | 12.6 | 11.55 | 10.5 | 9.45 | 8.4 | 7.35 | 6.3 | 5.25 | 4.2 | 3.15 | 2.1 | 1.05 | 0 | 23
1.05
|  | 44 | 44 | 42 | 42 | 42 | 39 | 37 | 35 | 35 | 32 | 32 | 32 | 29.5 | 29.5 | 28.5 | 28.5 | 26 | 24 | 24 | 23 | 23 | 23 | 19 | 19 | 19 | 19 | 16 | 16 | 14 | 10 | 10 | 10 | 7 | 6 | 5 | 5 | 2 | 1 | 1 | 1

## Sprint 3
Hours Spent
|  | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30
Story 19 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 2 | 0.5 | 7.5 | 7
Story 20 | 5.5 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1.5 | 2 | 5.5 | 5.5
Story 16 | 3 | 0 | 2 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
Story 17 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
Story 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 4 | 4
Story 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 4 | 4
Actual Hours Remaining | 27 | 27 | 25 | 20 | 20 | 20 | 20 | 15 | 11 | 3.5 | 0
Estimated Hours Remaining | 58 | 52.2 | 46.4 | 40.6 | 34.8 | 29 | 23.2 | 17.4 | 11.6 | 5.8 | 0

## Sprint 4
Hours Spent
|  | Day 31 | Day 32 | Day 33 | Day 34 | Day 35 | Day 36 | Day 37 | Day 38 | Day 39 | Day 40
Story 6 | 5.5 | 0 | 0 | 0 | 0 | 4 | 0 | 1.5 | 0 | 0 | 0 | 5.5
Story 7 | 5.5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 1.5 | 0 | 5.5
Story 3 (cont.) - improvements | 10 | 0 | 0 | 0 | 3 | 2 | 0 | 3 | 2 | 0 | 0 | 10
Story 21 | 4 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 4
Story 22 | 2.5 | 0 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5
Story 23 | 5 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Actual Hours Remaining | 32.5 | 32.5 | 30.5 | 28 | 22 | 12 | 11 | 6.5 | 1.5 | 0 | 0
Estimated Hours Remaining | 58 | 52.2 | 46.4 | 40.6 | 34.8 | 29 | 23.2 | 17.4 | 11.6 | 5.8 | 0

## Release 1 - Hours
Story Name | Task No | Task Description | Release Hours Remaining | Estimated Hours | Estimated Hours Remaining | Time Taken | Effort Hours Remaining
|  |  | 92 | 92 | 92 | 77 | 77 | 1.4375
Story 8 - Sprint 1 | T001 | Create a home page (customers view of website) | 90.5625 | 2 | 90 | 1.5 | 75.5 |  | 65
| T002 | Write test cases | 89.125 | 2 | 88 | 1 | 74.5 |  | 64
| T003 | Create login system for customers (connects to database) | 87.6875 | 3 | 85 | 3 | 71.5 |  | 63
| T004 | Create profile / shipping management page | 86.25 | 2 | 83 | 1 | 70.5 |  | 62
| T005 | Create table in the database to store pickup requests | 84.8125 | 0.5 | 82.5 | 0.5 | 70 |  | 61
| T006 | Create book shipment form | 83.375 | 1.5 | 81 | 1 | 69 |  | 60
| T007 | Write code to connect and submit to the database (pickup request table) | 81.9375 | 1 | 80 | 1 | 68 |  | 59
| T008 | Create page to show all pending shipments | 80.5 | 1.5 | 78.5 | 1 | 67 |  | 58
| T009 | Verify story is complete (acceptance criteria test) | 79.0625 | 1 | 77.5 | 1 | 66 |  | 57
Story 9 - Sprint 1 | T010 | Create a tracking page (customers view of website) | 77.625 | 1 | 76.5 | 1 | 65 |  | 56
| T011 | Write test cases | 76.1875 | 2 | 74.5 | 1.5 | 63.5 |  | 55
| T012 | Connecting to the database and selecting the unique tracking number. | 74.75 | 1 | 73.5 | 1 | 62.5 |  | 54
| T013 | Create page outputting the results of the tracking number in a visually appealing tabular format. | 73.3125 | 2 | 71.5 | 3 | 59.5 |  | 53
| T014 | Verify story is complete (acceptance criteria test) | 71.875 | 1 | 70.5 | 1 | 58.5 |  | 52
Story 10 - Sprint 1 | T015 | Create the pdf template for the consignment note. | 70.4375 | 1.5 | 69 | 2 | 56.5 |  | 51
| T016 | Write test cases. | 69 | 1 | 68 | 0.5 | 56 |  | 50
| T017 | Connect to database and select relevant information for the consignment note. | 67.5625 | 1 | 67 | 1 | 55 |  | 49
| T018 | Generate a printable copy of the consignment note. | 66.125 | 2 | 65 | 1 | 54 |  | 48
| T019 | Write code to save the consignment note to the database | 64.6875 | 2 | 63 | 1 | 53 |  | 47
| T020 | Verify story is complete (acceptance criteria test) | 63.25 | 1 | 62 | 1 | 52 |  | 46
Story 11 - Sprint 1 | T021 | Create the estimate shipping webpage. | 61.8125 | 1 | 61 | 1 | 51 |  | 45
| T022 | Write test cases. | 60.375 | 1 | 60 | 1 | 50 |  | 44
| T023 | Write code (formula) to calculate the shipping cost based off the information given in the form. | 58.9375 | 2 | 58 | 2.5 | 47.5 |  | 43
| T024 | Create page to output the results of the calculation | 57.5 | 0.5 | 57.5 | 0.5 | 47 |  | 42
| T025 | Verify story is complete (acceptance criteria test). | 56.0625 | 2 | 55.5 | 1.5 | 45.5 |  | 41
Story 12 - Sprint 1 | T026 | Create the pdf template for the tax invoice. | 54.625 | 1.5 | 54 | 2 | 43.5 |  | 40
| T027 | Write test cases. | 53.1875 | 1 | 53 | 0.5 | 43 |  | 39
| T028 | Connect to database and select relevant information for the tax invoice. | 51.75 | 1 | 52 | 1 | 42 |  | 38
| T029 | Generate a printable copy of the tax invoice. | 50.3125 | 2 | 50 | 0 | 42 |  | 37
| T030 | Write code to email a pdf copy of the invoice. | 48.875 | 2 | 48 | 2 | 40 |  | 36
| T031 | Write code to save the tax invoice to the database | 47.4375 | 2 | 46 | 0.5 | 39.5 |  | 35
| T032 | Verify story is complete (acceptance criteria test). | 46 | 1 | 45 | 1 | 38.5 |  | 34
Story 14 - Sprint 1 | T033 | Create registration page (where users registers). | 44.5625 | 1.5 | 43.5 | 2 | 36.5 |  | 33
| T034 | Write test cases. | 43.125 | 2 | 41.5 | 1 | 35.5 |  | 32
| T035 | Write code to submit the registration information to the database | 41.6875 | 2 | 39.5 | 1.5 | 34 |  | 31
| T036 | Create a personal profile page and write code to retrieve user details from the database. | 40.25 | 2 | 37.5 | 1 | 33 |  | 30
| T037 | Write code to retrieve the user information from the database and output it to the “make a booking” page. | 38.8125 | 2.5 | 35 | 2.5 | 30.5 |  | 29
| T038 | Verify story is complete (acceptance criteria test). | 37.375 | 1 | 34 | 1 | 29.5 |  | 28
Story 1 - Sprint 2 | T039 | Create dashboard portal for employees | 35.9375 | 3 | 31 | 2 | 27.5 |  | 27
| T040 | Write test cases. | 34.5 | 2 | 29 | 0.5 | 27 |  | 26
| T041 | Create page within the dashboard for displaying a list of contacts. | 33.0625 | 2 | 27 | 1 | 26 |  | 25
| T042 | Create customers table within the database to store their details. | 31.625 | 0.5 | 26.5 | 0.5 | 25.5 |  | 24
| T043 | Write code to connect to the database and output the results in a list. | 30.1875 | 1 | 25.5 | 1 | 24.5 |  | 23
| T044 | Use plugin to create pagination for data | 28.75 | 1 | 24.5 | 0.5 | 24 |  | 22
| T045 | Create page within the dashboard for displaying all the data related to a single customer | 27.3125 | 2 | 22.5 | 1.5 | 22.5 |  | 21
| T046 | Verify story is complete (acceptance criteria test). | 25.875 | 1 | 21.5 | 0.5 | 22 |  | 20
Story 4 - Sprint 2 | T047 | Create page within the dashboard for displaying a list of shipments - with pagination plugin. | 24.4375 | 2 | 19.5 | 2 | 20 |  | 19
| T048 | Write test cases. | 23 | 2 | 17.5 | 1 | 19 |  | 18
| T049 | Write code to connect to the database and output the shipment results in a list. | 21.5625 | 0.5 | 17 | 0.5 | 18.5 |  | 17
| T050 | Create a page within the dashboard for displaying all the data related to a single shipment (individual shipment page) | 20.125 | 2 | 15 | 2 | 16.5 |  | 16
| T051 | Create a page within the dashboard to give the user the option to update the status. | 18.6875 | 1 | 14 | 1 | 15.5 |  | 15
| T052 | Write code to modify the shipment status in the database | 17.25 | 0.5 | 13.5 | 1 | 14.5 |  | 14
| T053 | Verify story is complete (acceptance criteria test). | 15.8125 | 1 | 12.5 | 1 | 13.5 |  | 13
Story 5 - Sprint 2 | T054 | Create page within the dashboard for displaying a list of payments - with pagination plugin. | 14.375 | 2 | 10.5 | 1.5 | 12 |  | 12
| T055 | Write test cases. | 12.9375 | 1 | 9.5 | 0.5 | 11.5 |  | 11
| T056 | Write code to connect to the database and output the payment results in a list. | 11.5 | 0.5 | 9 | 0.5 | 11 |  | 10
| T057 | Create a page within the dashboard to give the user the option to update the status of the payment. | 10.0625 | 1 | 8 | 1 | 10 |  | 9
| T058 | Write code to modify the payment status in the database | 8.625 | 0.5 | 7.5 | 1 | 9 |  | 8
| T059 | Verify story is complete (acceptance criteria test). | 7.1875 | 1 | 6.5 | 1 | 8 |  | 7
Story 18 - Sprint 2 | T060 | Create page within the dashboard for displaying a list of all pending pickups and package drop offs - with pagination plugin (table sorted by postcode). | 5.75 | 2 | 4.5 | 0.5 | 7.5 |  | 6
| T061 | Write test cases. | 4.3125 | 1 | 3.5 | 0.5 | 7 |  | 5
| T062 | Create a page to assign certain deliveries or pickups to a single driver. | 2.875 | 2 | 1.5 | 6 | 1 |  | 4
| T063 | Write code to modify the shipment data in the database to reflect the employee’s id. | 1.4375 | 0.5 | 1 | 0.5 | 0.5 |  | 3
| T064 | Write code to send an automatic notification to the driver that they have been assigned pickups or deliveries. | 0 | 1 | 0 | 0.5 | 0 |  | 2
[6 empty] | 77 |  |  | 1
0

## Release 2 - Hours
Story Name | Task No | Task Description | Status | Assigned To | Project Hours Remaining | Estimated Hours | Estimated Hours Remaining | Time Taken | Effort Hours Remaining
[5 empty] | 61 | 61 | 61 | 54.5 | 54.5 | 1.1731
Story 19 - Sprint 3 | T065 | Write test cases. | Closed | Matthew | 59.8269 | 1 | 60 | 1 | 53.5 |  | 53
| T066 | Create expenses page where the coordinator can view all expenses. | Closed |  | 58.6538 | 1.5 | 58.5 | 1.5 | 52 |  | 52
| T067 | Create a table within the database which stores expenses | Closed |  | 57.4808 | 0.5 | 58 | 0.5 | 51.5 |  | 51
| T068 | Create a php connection on the expenses page to output all of the expenses within the expenses table. | Closed |  | 56.3077 | 0.5 | 57.5 | 1 | 50.5 |  | 50
| T069 | Create a page with a form where the coordinator can add expenses incurred by employees. | Closed |  | 55.1346 | 1 | 56.5 | 0.5 | 50 |  | 49
| T070 | Create a page that submits data that is entered into the form to the database, which redirects back to the expenses page. | Closed |  | 53.9615 | 1 | 55.5 | 1 | 49 |  | 48
| T071 | Verify story is complete (acceptance criteria test). | Closed |  | 52.7885 | 0.5 | 55 | 0.5 | 48.5 |  | 47
Story 20 - Sprint 3 | T072 | Create page within the dashboard with forms for a pickup request. | Closed | Reeve | 51.6154 | 2 | 53 | 2 | 46.5 |  | 46
| T073 | Create table in the database and write code to connect and store the information entered into the form. | Closed |  | 50.4423 | 2 | 51 | 1.5 | 45 |  | 45
| T074 | Create page to display a list of existing requests | Closed |  | 49.2692 | 1.5 | 49.5 | 1 | 44 |  | 44
| T075 | Write test cases. | Closed |  | 48.0962 | 1 | 48.5 | 0.5 | 43.5 |  | 43
| T076 | Verify story is complete (acceptance criteria test). | Closed |  | 46.9231 | 1 | 47.5 | 0.5 | 43 |  | 42
Story 16 - Sprint 3 | T077 | Create a page within the Coordinator Dashboard to allow the Coordinator to send notifications. | Closed | Samuel | 45.75 | 3 | 44.5 | 1.5 | 41.5 |  | 41
| T078 | Create a script capable of taking data submitted by the notification creator page and sending it to all receivers. | Closed |  | 44.5769 | 1.5 | 43 | 1 | 40.5 |  | 40
| T079 | Write Test Cases | Closed |  | 43.4038 | 1 | 42 | 1 | 39.5 |  | 39
| T080 | Verify story is complete (acceptance criteria test). | Closed |  | 42.2308 | 1 | 41 | 1 | 38.5 |  | 38
Story 17 - Sprint 3 | T081 | Create a page within the Coordinator Dashboard to allow the Coordinator to send emergency notifications. | Closed | Samuel | 41.0577 | 3 | 38 | 1.5 | 37 |  | 37
| T082 | Create a script capable of taking data submitted by the notification creator page and sending it to all receivers. | Closed |  | 39.8846 | 1.5 | 36.5 | 1 | 36 |  | 36
| T083 | Write Test Cases | Closed |  | 38.7115 | 1 | 35.5 | 1 | 35 |  | 35
| T084 | Verify story is complete (acceptance criteria test). | Closed |  | 37.5385 | 1 | 34.5 | 1 | 34 |  | 34
Story 3 - Sprint 4 | T085 | Write tracking page where coordinator can track the packages | Closed | Veronica | 36.3654 | 3 | 31.5 | 3 | 31 |  | 33
| T086 | Write test cases | Closed |  | 35.1923 | 1 | 30.5 | 1 | 30 |  | 32
| T087 | Include the pages in the sidebar | Closed |  | 34.0192 | 0.5 | 30 | 0.5 | 29.5 |  | 31
| T088 | Write the driver journey page where the driver can notify the start and end time of their journey | In Progress |  | 32.8462 | 3 | 27 | 4 | 25.5 |  | 30
| T089 | Create the buttons for start and end time | In Progress |  | 31.6731 | 0.5 | 26.5 | 1 | 24.5 |  | 29
| T090 | Create a table within the database for the start and end button of the driver's journey | In Progress |  | 30.5 | 1 | 25.5 | 1 | 23.5 |  | 28
| T091 | Verify story is complete (acceptance criteria test). | In Progress |  | 29.3269 | 1 | 24.5 | 1 | 22.5 |  | 27
Story 21 - Sprint 4 | T092 | Create a page for drivers to check what shift they are rostered on for the following two weeks | Closed | Hayden | 28.1538 | 1 | 23.5 | 1 | 21.5 |  | 26
| T093 | Have driver page autofill based on login credentials | Closed |  | 26.9808 |  | 23.5 |  | 21.5 |  | 25
| T094 | Create a page for the coordinator to view the shifts for all of the employees | Closed |  | 25.8077 | 1 | 22.5 | 0.5 | 21 |  | 24
| T095 | Allow the coordinator to change the shifts of the drivers. | Closed |  | 24.6346 | 2 | 20.5 | 2.5 | 18.5 |  | 23
Story 6 - Sprint 4 | T096 | Create a page where drivers are able to view all deliveries filtered by day and ordered by delivery time. | Closed | Samuel | 23.4615 | 4 | 16.5 | 3 | 15.5 |  | 22
| T097 | Modify the database to store the additional data needed for this page. | Closed |  | 22.2885 | 0.5 | 16 | 1 | 14.5 |  | 21
| T098 | Incorporate page into driver dashboard. | Closed |  | 21.1154 | 0.5 | 15.5 | 0.5 | 14 |  | 20
| T099 | Write test cases. | Closed |  | 19.9423 | 0.5 | 15 | 0.5 | 13.5 |  | 19
| T100 | Verify story is complete (acceptance criteria test). | Closed |  | 18.7692 | 0.5 | 14.5 | 0.5 | 13 |  | 18
Story 7 -Sprint 4 | T101 | Create an overview page to view a list of deliveries | Closed | Reeve | 17.5962 | 0.5 | 14 | 0.5 | 12.5 |  | 17
| T102 | Write test cases. | Closed |  | 16.4231 | 0.5 | 13.5 | 0.5 | 12 |  | 16
| T103 | Create a link to the database that retrieves the assigned deliveries. | Closed |  | 15.25 | 0.5 | 13 | 0.5 | 11.5 |  | 15
| T104 | Create a table to outputs the retrieved data. | Closed |  | 14.0769 | 1 | 12 | 1 | 10.5 |  | 14
| T105 | Verify story is complete (acceptance criteria test). | Closed |  | 12.9038 | 0.5 | 11.5 | 0.5 | 10 |  | 13
| T106 | Refine the work done on the contacts list and page done in sprint 2. | Closed |  | 11.7308 | 1 | 10.5 | 1 | 9 |  | 12
| T107 | Finish the manual bookings page for the coordinator in sprint 3 | Closed |  | 10.5577 | 2 | 8.5 | 1.5 | 7.5 |  | 11
Story 22 - Sprint 4 | T108 | Add a table module on the dashboard to display saved tracking number. | Closed | Matthew | 9.3846 | 0.5 | 8 | 0.5 | 7 |  | 10
| T109 | Create a connection to the database that pulls saved tracking numbers | Closed |  | 8.2115 | 0.5 | 7.5 | 0.5 | 6.5 |  | 9
| T110 | Write code to output the retrieved tracking numbers. | Closed |  | 7.0385 | 1 | 6.5 | 0.5 | 6 |  | 8
| T111 | Verify story is complete (acceptance criteria test). | Closed |  | 5.8654 | 1 | 5.5 | 1 | 5 |  | 7
Story 23 - Sprint 4 | T112 | Creating page within the driver dashboard that the driver can type in the connote number and get results back. | Closed | Matthew | 4.6923 | 1 | 4.5 | 1 | 4 |  | 6
| T113 | Write test cases. | Closed |  | 3.5192 | 1 | 3.5 | 1 | 3 |  | 5
| T114 | Create a link to the database that retrieves all details about the package based off the connote number. | Closed |  | 2.3462 | 1 | 2.5 | 1 | 2 |  | 4
| T115 | Implement a way for the driver to update the packages status in the database. | Closed |  | 1.1731 | 2 | 0.5 | 1.5 | 0.5 |  | 3
| T116 | Verify story is complete (acceptance criteria test). | Closed |  | 0 | 0.5 | 0 | 0.5 | 0 |  | 2
1
0

## Assigned Stories
Story Name | Task No | Task Description | Status | Assigned To | Project Hours Remaining | Estimated Hours | Estimated Hours Remaining | Time Taken | Effort Hours Remaining
[5 empty] | 153 | 153 | 153 | 131.5 | 131.5 | 1.319
Story 8 - Sprint 1 | T001 | Create a home page (customers view of website) | Closed | Matthew | 151.681 | 2 | 151 | 1.5 | 130 |  | T116
| T002 | Write test cases | Closed |  | 150.3621 | 2 | 149 | 1 | 129 |  | T115
| T003 | Create login system for customers (connects to database) | Closed |  | 149.0431 | 3 | 146 | 3 | 126 |  | T114
| T004 | Create profile / shipping management page | Closed |  | 147.7241 | 2 | 144 | 1 | 125 |  | T113
| T005 | Create table in the database to store pickup requests | Closed |  | 146.4051 | 0.5 | 143.5 | 0.5 | 124.5 |  | T112
| T006 | Create book shipment form | Closed |  | 145.0862 | 1.5 | 142 | 1 | 123.5 |  | T111
| T007 | Write code to connect and submit to the database (pickup request table) | Closed |  | 143.7672 | 1 | 141 | 1 | 122.5 |  | T110
| T008 | Create page to show all pending shipments | Closed |  | 142.4482 | 1.5 | 139.5 | 1 | 121.5 |  | T109
| T009 | Verify story is complete (acceptance criteria test) | Closed |  | 141.1293 | 1 | 138.5 | 1 | 120.5 |  | T108
Story 9 - Sprint 1 | T010 | Create a tracking page (customers view of website) | Closed | Veronica | 139.8103 | 1 | 137.5 | 1 | 119.5 |  | T107
| T011 | Write test cases | Closed |  | 138.4913 | 2 | 135.5 | 1.5 | 118 |  | T106
| T012 | Connecting to the database and selecting the unique tracking number. | Closed |  | 137.1724 | 1 | 134.5 | 1 | 117 |  | T105
| T013 | Create page outputting the results of the tracking number in a visually appealing tabular format. | Closed |  | 135.8534 | 2 | 132.5 | 3 | 114 |  | T104
| T014 | Verify story is complete (acceptance criteria test) | Closed |  | 134.5344 | 1 | 131.5 | 1 | 113 |  | T103
Story 10 - Sprint 1 | T015 | Create the pdf template for the consignment note. | Closed | Hayden | 133.2154 | 1.5 | 130 | 2 | 111 |  | T102
| T016 | Write test cases. | Closed |  | 131.8965 | 1 | 129 | 0.5 | 110.5 |  | T101
| T017 | Connect to database and select relevant information for the consignment note. | Closed |  | 130.5775 | 1 | 128 | 1 | 109.5 |  | T100
| T018 | Generate a printable copy of the consignment note. | Closed |  | 129.2585 | 2 | 126 | 1 | 108.5 |  | T99
| T019 | Write code to save the consignment note to the database | Closed |  | 127.9396 | 2 | 124 | 1 | 107.5 |  | T98
| T020 | Verify story is complete (acceptance criteria test) | Closed |  | 126.6206 | 1 | 123 | 1 | 106.5 |  | T97
Story 11 - Sprint 1 | T021 | Create the estimate shipping webpage. | Closed | Reeve | 125.3016 | 1 | 122 | 1 | 105.5 |  | T96
| T022 | Write test cases. | Closed |  | 123.9827 | 1 | 121 | 1 | 104.5 |  | T95
| T023 | Write code (formula) to calculate the shipping cost based off the information given in the form. | Closed |  | 122.6637 | 2 | 119 | 2.5 | 102 |  | T94
| T024 | Create page to output the results of the calculation | Closed |  | 121.3447 | 0.5 | 118.5 | 0.5 | 101.5 |  | T93
| T025 | Verify story is complete (acceptance criteria test). | Closed |  | 120.0257 | 2 | 116.5 | 1.5 | 100 |  | T92
Story 12 - Sprint 1 | T026 | Create the pdf template for the tax invoice. | Closed | Hayden | 118.7068 | 1.5 | 115 | 2 | 98 |  | T91
| T027 | Write test cases. | Closed |  | 117.3878 | 1 | 114 | 0.5 | 97.5 |  | T90
| T028 | Connect to database and select relevant information for the tax invoice. | Closed |  | 116.0688 | 1 | 113 | 1 | 96.5 |  | T89
| T029 | Generate a printable copy of the tax invoice. | Closed |  | 114.7499 | 2 | 111 | 0 | 96.5 |  | T88
| T030 | Write code to email a pdf copy of the invoice. | Closed |  | 113.4309 | 2 | 109 | 2 | 94.5 |  | T87
| T031 | Write code to save the tax invoice to the database | Closed |  | 112.1119 | 2 | 107 | 0.5 | 94 |  | T86
| T032 | Verify story is complete (acceptance criteria test). | Closed |  | 110.793 | 1 | 106 | 1 | 93 |  | T85
Story 14 - Sprint 1 | T033 | Create registration page (where users registers). | Closed | Samuel | 109.474 | 1.5 | 104.5 | 2 | 91 |  | T84
| T034 | Write test cases. | Closed |  | 108.155 | 2 | 102.5 | 1 | 90 |  | T83
| T035 | Write code to submit the registration information to the database | Closed |  | 106.836 | 2 | 100.5 | 1.5 | 88.5 |  | T82
| T036 | Create a personal profile page and write code to retrieve user details from the database. | Closed |  | 105.5171 | 2 | 98.5 | 1 | 87.5 |  | T81
| T037 | Write code to retrieve the user information from the database and output it to the “make a booking” page. | Closed |  | 104.1981 | 2.5 | 96 | 2.5 | 85 |  | T80
| T038 | Verify story is complete (acceptance criteria test). | Closed |  | 102.8791 | 1 | 95 | 1 | 84 |  | T79
Story 1 - Sprint 2 | T039 | Create dashboard portal for employees | Closed | Reeve | 101.5602 | 3 | 92 | 2 | 82 |  | T78
| T040 | Write test cases. | Closed |  | 100.2412 | 2 | 90 | 0.5 | 81.5 |  | T77
| T041 | Create page within the dashboard for displaying a list of contacts. | Closed |  | 98.9222 | 2 | 88 | 1 | 80.5 |  | T76
| T042 | Create customers table within the database to store their details. | Closed |  | 97.6033 | 0.5 | 87.5 | 0.5 | 80 |  | T75
| T043 | Write code to connect to the database and output the results in a list. | Closed |  | 96.2843 | 1 | 86.5 | 1 | 79 |  | T74
| T044 | Use plugin to create pagination for data | Closed |  | 94.9653 | 1 | 85.5 | 0.5 | 78.5 |  | T73
| T045 | Create page within the dashboard for displaying all the data related to a single customer | Closed |  | 93.6464 | 2 | 83.5 | 1.5 | 77 |  | T72
| T046 | Verify story is complete (acceptance criteria test). | Closed |  | 92.3274 | 1 | 82.5 | 0.5 | 76.5 |  | T71
Story 4 - Sprint 2 | T047 | Create page within the dashboard for displaying a list of shipments - with pagination plugin. | Closed | Veronica | 91.0084 | 2 | 80.5 | 2 | 74.5 |  | T70
| T048 | Write test cases. | Closed |  | 89.6894 | 2 | 78.5 | 1 | 73.5 |  | T69
| T049 | Write code to connect to the database and output the shipment results in a list. | Closed |  | 88.3705 | 0.5 | 78 | 0.5 | 73 |  | T68
| T050 | Create a page within the dashboard for displaying all the data related to a single shipment (individual shipment page) | Closed |  | 87.0515 | 2 | 76 | 2 | 71 |  | T67
| T051 | Create a page within the dashboard to give the user the option to update the status. | Closed |  | 85.7325 | 1 | 75 | 1 | 70 |  | T66
| T052 | Write code to modify the shipment status in the database | Closed |  | 84.4136 | 0.5 | 74.5 | 1 | 69 |  | T65
| T053 | Verify story is complete (acceptance criteria test). | Closed |  | 83.0946 | 1 | 73.5 | 1 | 68 |  | T64
Story 5 - Sprint 2 | T054 | Create page within the dashboard for displaying a list of payments - with pagination plugin. | Closed | Hayden | 81.7756 | 2 | 71.5 | 1.5 | 66.5 |  | T63
| T055 | Write test cases. | Closed |  | 80.4567 | 1 | 70.5 | 0.5 | 66 |  | T62
| T056 | Write code to connect to the database and output the payment results in a list. | Closed |  | 79.1377 | 0.5 | 70 | 0.5 | 65.5 |  | T61
| T057 | Create a page within the dashboard to give the user the option to update the status of the payment. | Closed |  | 77.8187 | 1 | 69 | 1 | 64.5 |  | T60
| T058 | Write code to modify the payment status in the database | Closed |  | 76.4997 | 0.5 | 68.5 | 1 | 63.5 |  | T59
| T059 | Verify story is complete (acceptance criteria test). | Closed |  | 75.1808 | 1 | 67.5 | 1 | 62.5 |  | T58
Story 18 - Sprint 2 | T060 | Create page within the dashboard for displaying a list of all pending pickups and package drop offs - with pagination plugin (table sorted by postcode). | Closed | Samuel | 73.8618 | 2 | 65.5 | 0.5 | 62 |  | T57
| T061 | Write test cases. | Closed |  | 72.5428 | 1 | 64.5 | 0.5 | 61.5 |  | T56
| T062 | Create a page to assign certain deliveries or pickups to a single driver. | Closed |  | 71.2239 | 2 | 62.5 | 6 | 55.5 |  | T55
| T063 | Write code to modify the shipment data in the database to reflect the employee’s id. | Closed |  | 69.9049 | 0.5 | 62 | 0.5 | 55 |  | T54
| T064 | Write code to send an automatic notification to the driver that they have been assigned pickups or deliveries. | Closed |  | 68.5859 | 1 | 61 | 0.5 | 54.5 |  | T53
Story 19 - Sprint 3 | T065 | Write test cases. | Closed | Matthew | 67.267 | 1 | 60 | 1 | 53.5 |  | T52
| T066 | Create expenses page where the coordinator can view all expenses. | Closed |  | 65.948 | 1.5 | 58.5 | 1.5 | 52 |  | T51
| T067 | Create a table within the database which stores expenses | Closed |  | 64.629 | 0.5 | 58 | 0.5 | 51.5 |  | T50
| T068 | Create a php connection on the expenses page to output all of the expenses within the expenses table. | Closed |  | 63.31 | 0.5 | 57.5 | 1 | 50.5 |  | T49
| T069 | Create a page with a form where the coordinator can add expenses incurred by employees. | Closed |  | 61.9911 | 1 | 56.5 | 0.5 | 50 |  | T48
| T070 | Create a page that submits data that is entered into the form to the database, which redirects back to the expenses page. | Closed |  | 60.6721 | 1 | 55.5 | 1 | 49 |  | T47
| T071 | Verify story is complete (acceptance criteria test). | Closed |  | 59.3531 | 0.5 | 55 | 0.5 | 48.5 |  | T46
Story 20 - Sprint 3 | T072 | Create page within the dashboard with forms for a pickup request. | Closed | Reeve | 58.0342 | 2 | 53 | 2 | 46.5 |  | T45
| T073 | Create table in the database and write code to connect and store the information entered into the form. | Closed |  | 56.7152 | 2 | 51 | 1.5 | 45 |  | T44
| T074 | Create page to display a list of existing requests | Closed |  | 55.3962 | 1.5 | 49.5 | 1 | 44 |  | T43
| T075 | Write test cases. | Closed |  | 54.0773 | 1 | 48.5 | 0.5 | 43.5 |  | T42
| T076 | Verify story is complete (acceptance criteria test). | Closed |  | 52.7583 | 1 | 47.5 | 0.5 | 43 |  | T41
Story 16 - Sprint 3 | T077 | Create a page within the Coordinator Dashboard to allow the Coordinator to send notifications. | Closed | Samuel | 51.4393 | 3 | 44.5 | 1.5 | 41.5 |  | T40
| T078 | Create a script capable of taking data submitted by the notification creator page and sending it to all receivers. | Closed |  | 50.1203 | 1.5 | 43 | 1 | 40.5 |  | T39
| T079 | Write Test Cases | Closed |  | 48.8014 | 1 | 42 | 1 | 39.5 |  | T38
| T080 | Verify story is complete (acceptance criteria test). | Closed |  | 47.4824 | 1 | 41 | 1 | 38.5 |  | T37
Story 17 - Sprint 3 | T081 | Create a page within the Coordinator Dashboard to allow the Coordinator to send emergency notifications. | Closed | Samuel | 46.1634 | 3 | 38 | 1.5 | 37 |  | T36
| T082 | Create a script capable of taking data submitted by the notification creator page and sending it to all receivers. | Closed |  | 44.8445 | 1.5 | 36.5 | 1 | 36 |  | T35
| T083 | Write Test Cases | Closed |  | 43.5255 | 1 | 35.5 | 1 | 35 |  | T34
| T084 | Verify story is complete (acceptance criteria test). | Closed |  | 42.2065 | 1 | 34.5 | 1 | 34 |  | T33
Story 3 - Sprint 4 | T085 | Write tracking page where coordinator can track the packages | Closed | Veronica | 40.8876 | 3 | 31.5 | 3 | 31 |  | T32
| T086 | Write test cases | Closed |  | 39.5686 | 1 | 30.5 | 1 | 30 |  | T31
| T087 | Include the pages in the sidebar | Closed |  | 38.2496 | 0.5 | 30 | 0.5 | 29.5 |  | T30
| T088 | Write the driver journey page where the driver can notify the start and end time of their journey | In Progress |  | 36.9306 | 3 | 27 | 4 | 25.5 |  | T29
| T089 | Create the buttons for start and end time | In Progress |  | 35.6117 | 0.5 | 26.5 | 1 | 24.5 |  | T28
| T090 | Create a table within the database for the start and end button of the driver's journey | In Progress |  | 34.2927 | 1 | 25.5 | 1 | 23.5 |  | T27
| T091 | Verify story is complete (acceptance criteria test). | In Progress |  | 32.9737 | 1 | 24.5 | 1 | 22.5 |  | T26
Story 21 - Sprint 4 | T092 | Create a page for drivers to check what shift they are rostered on for the following two weeks | Closed | Hayden | 31.6548 | 1 | 23.5 | 1 | 21.5 |  | T25
| T093 | Have driver page autofill based on login credentials | Closed |  | 30.3358 |  | 23.5 |  | 21.5 |  | T24
| T094 | Create a page for the coordinator to view the shifts for all of the employees | Closed |  | 29.0168 | 1 | 22.5 | 0.5 | 21 |  | T23
| T095 | Allow the coordinator to change the shifts of the drivers. | Closed |  | 27.6979 | 2 | 20.5 | 2.5 | 18.5 |  | T22
Story 6 - Sprint 4 | T096 | Create a page where drivers are able to view all deliveries filtered by day and ordered by delivery time. | Closed | Samuel | 26.3789 | 4 | 16.5 | 3 | 15.5 |  | T21
| T097 | Modify the database to store the additional data needed for this page. | Closed |  | 25.0599 | 0.5 | 16 | 1 | 14.5 |  | T20
| T098 | Incorporate page into driver dashboard. | Closed |  | 23.7409 | 0.5 | 15.5 | 0.5 | 14 |  | T19
| T099 | Write test cases. | Closed |  | 22.422 | 0.5 | 15 | 0.5 | 13.5 |  | T18
| T100 | Verify story is complete (acceptance criteria test). | Closed |  | 21.103 | 0.5 | 14.5 | 0.5 | 13 |  | T17
Story 7 -Sprint 4 | T101 | Create an overview page to view a list of deliveries | Closed | Reeve | 19.784 | 0.5 | 14 | 0.5 | 12.5 |  | T16
| T102 | Write test cases. | Closed |  | 18.4651 | 0.5 | 13.5 | 0.5 | 12 |  | T15
| T103 | Create a link to the database that retrieves the assigned deliveries. | Closed |  | 17.1461 | 0.5 | 13 | 0.5 | 11.5 |  | T14
| T104 | Create a table to outputs the retrieved data. | Closed |  | 15.8271 | 1 | 12 | 1 | 10.5 |  | T13
| T105 | Verify story is complete (acceptance criteria test). | Closed |  | 14.5082 | 0.5 | 11.5 | 0.5 | 10 |  | T12
| T106 | Refine the work done on the contacts list and page done in sprint 2. | Closed |  | 13.1892 | 1 | 10.5 | 1 | 9 |  | T11
| T107 | Finish the manual bookings page for the coordinator in sprint 3 | Closed |  | 11.8702 | 2 | 8.5 | 1.5 | 7.5 |  | T10
Story 22 - Sprint 4 | T108 | Add a table module on the dashboard to display saved tracking number. | Closed | Matthew | 10.5512 | 0.5 | 8 | 0.5 | 7 |  | T9
| T109 | Create a connection to the database that pulls saved tracking numbers | Closed |  | 9.2323 | 0.5 | 7.5 | 0.5 | 6.5 |  | T8
| T110 | Write code to output the retrieved tracking numbers. | Closed |  | 7.9133 | 1 | 6.5 | 0.5 | 6 |  | T7
| T111 | Verify story is complete (acceptance criteria test). | Closed |  | 6.5943 | 1 | 5.5 | 1 | 5 |  | T6
Story 23 - Sprint 4 | T112 | Creating page within the driver dashboard that the driver can type in the connote number and get results back. | Closed | Matthew | 5.2754 | 1 | 4.5 | 1 | 4 |  | T5
| T113 | Write test cases. | Closed |  | 3.9564 | 1 | 3.5 | 1 | 3 |  | T4
| T114 | Create a link to the database that retrieves all details about the package based off the connote number. | Closed |  | 2.6374 | 1 | 2.5 | 1 | 2 |  | T3
| T115 | Implement a way for the driver to update the packages status in the database. | Closed |  | 1.3185 | 2 | 0.5 | 1.5 | 0.5 |  | T2
| T116 | Verify story is complete (acceptance criteria test). | Closed |  | 0 | 0.5 | 0 | 0.5 | 0 |  | T1