## 25-07-2016
Meeting Minutes
Date: 25/07/2016 | Week 1
Agenda Items | Discussion Points | Action Required | Assigned Person | Due Date
This was our first meeting where we formed groups no meeting minutes were recorded
Attendance: Matthew, Veronica, Reeve, Samuel

## 01-08-2016
Meeting Minutes
Date: 01/08/2016 | Week 2
Agenda Items | Discussion Points | Action Required | Assigned Person | Due Date
Decide on Project Task | As a group we voted on the project. We decided to complete the courier management system. | - | - | -
Meet Client Team | We met our client team and discussed the project. | - | - | -
Reading client description | As a team we read the case study/project description | - | - | -
Assigning Tasks | Each team member must summarise the basic features required within the application. | Summaries basic features of the website | All team members | 1996-08-08
Attendance: Matthew, Veronica, Reeve, Samuel

## 08-08-2016
Meeting Minutes
Date: 08/08/2016 | Week 3
Agenda Items | Discussion Points | Action Required | Assigned Person | Due Date
Summaries task requirements | We went through each person's project summary and compiled a list of the project requirements
Get approval | We then passed the requirements onto the client team for approval.
Begin work on user stories | Finally, we began to work on producing user stories and acceptance criteria | Finish user stories | All team members | 2016-08-15
Attendance: Matthew, Veronica, Reeve, Samuel, Hayden

## 15-08-2016
Meeting Minutes
Date:15/08/2016 | Week 4
Agenda Items | Discussion Points | Action Required | Assigned Person | Due Date
Receive feedback on task requirement | We met with the client team and received their feedback on our project summary
Receive feedback on user stories | After receiving out project summary feedback we explained our user stories. They said that the user stories and acceptance criteria were acceptable. They then helped us with assigning priorities to the the stories
Begin work on sprint and release documents | We began work on the sprint and release documents and assigned tasks to finish by next week | Finish release and sprint plans | Matthew | 2016-08-22
|  | Finalise user stories and write descriptions for sprints and releases | Veronica, Reeve, Samuel, Hayden | 2016-08-22
Attendance: Matthew, Veronica, Reeve, Samuel, Hayden

## 22-08-2016
Meeting Minutes
Date:22/08/2016 | Week 5
Agenda Items | Discussion Points | Action Required | Assigned Person | Due Date
Finalise Planning and Documentation | We met as a group and finalised the release and sprint planning
Meet with clients | We showed the release documents to the clients and ensured that the plan was acceptable
Assignment of Story Tasks | Story 8 | Complete work for story | Matthew | 2016-09-05
| Story 9 | Complete work for story | Veronica | 2016-09-05
| Story 10 | Complete work for story | Hayden | 2016-09-05
| Story 11 | Complete work for story | Reeve | 2016-09-05
| Story 12 | Complete work for story | Hayden | 2016-09-05
| Story 14 | Complete work for story | Samuel | 2016-09-05
Attendance: Matthew, Veronica, Reeve, Samuel, Hayden

## 29-08-2016
Meeting Minutes
Date:29/08/2016 | Week 6
Agenda Items | Discussion Points | Action Required | Assigned Person | Due Date
Check in | We met as a group showed the team the work completed thus far.
Continue working on Story | We individually continued working on our assigned story, bouncing ideas off each other to improve and unify the website
Stories Due | - | Complete work for story | All team members | 2016-09-05
Attendance: Matthew, Veronica, Reeve, Samuel, Hayden

## 05-09-2016
Meeting Minutes
Date:05/09/2016 | Week 7
Agenda Items | Discussion Points | Action Required | Assigned Person | Due Date
Demonstrate work to clients | We met with out clients and demonstrated work completed in Sprint 1
Assignment of Story Tasks | Story 1 | Complete work for story | Reeve | 2016-09-19
| Story 4 | Complete work for story | Veronica | 2016-09-19
| Story 5 | Complete work for story | Hayden | 2016-09-19
| Story 18 | Complete work for story | Reeve | 2016-09-19
| Work on the visuals of the website, along with the visuals of the dashboards | Complete work for website | Matthew | 2016-09-19
Writing business letter | Then we began writing the business letter (us as clients), we split up the sections and wrote them individually | Complete business letter | All team members | 2016-09-08
Attendance: Matthew, Veronica, Reeve, Samuel, Hayden

## 12-09-2016
Meeting Minutes
Date:12/09/2016 | Week 8
Agenda Items | Discussion Points | Action Required | Assigned Person | Due Date
Check in | We met as a group showed the team the work completed thus far.
Continue working on Story | We individually continued working on our assigned story, bouncing ideas off each other to improve and unify the website.
Discuss changes to sprint plan | We met with the client team to dicuss changes to user story 1. During development the functionality given in the user story was deemed inappropriate due to privacy concerns over an employee having access to customer's details and the owner being able to create a record of a customer without their consent. The client agreed and different criteria were set.
Stories Due | - | Complete work for story | All team members | 2016-09-19
Attendance: Matthew, Veronica, Reeve, Samuel, Hayden

## 19-09-2016
Meeting Minutes
Date:19/09/2016 | Week 9
Agenda Items | Discussion Points | Action Required | Assigned Person | Due Date
Demonstrate work to clients | We met with out clients and demonstrated work completed in Release 1 / Sprint 2
Assignment of Story Tasks | Story 19 | Complete work for story | Matthew | 2016-10-10
| Story 20 | Complete work for story | Reeve | 2016-10-10
| Story 16 | Complete work for story | Samuel | 2016-10-10
| Story 17 | Complete work for story | Samuel | 2016-10-10
| Story 3 | Complete work for story | Veronica | 2016-10-10
Attendance: Matthew, Veronica, Reeve, Samuel, Hayden

## 03-10-2016
Meeting Minutes
Date:03/10/2016 | Week 10
Agenda Items | Discussion Points | Action Required | Assigned Person | Due Date
No physical meeting due to public holiday. We checked in over skype - no meeting minutes were kept.

## 10-10-2016
Meeting Minutes
Date:10/10/2016 | Week 11
Agenda Items | Discussion Points | Action Required | Assigned Person | Due Date
Demonstrate work to clients | We met with out clients and demonstrated work completed in Sprint 3
Discussing changes to website | We then quickly sat down with the clients and discussed a change to the sprint/release planning process. We discussed the removal of story 13 due to it not adding very much business value. And replacing it with a story that assisted the drivers with delivering and picking up packages. Upon discussion they agreed that this was the right move. Similarly, Story 2 was considered too small to be made into its own site and it was decided with the client team that it would be more efficient for this functionality to be added to the assignments page. We proceeded with development
Assignment of Story Tasks | Story 21 | Complete work for story | Hayden | 2016-10-24
| Story 6 | Complete work for story | Samuel | 2016-10-24
| Story 7 | Complete work for story | Reeve | 2016-10-24
| Story 22 | Complete work for story | Matthew | 2016-10-24
| Story 23 | Complete work for story | Matthew | 2016-10-24
Writing business letter | Then we began writing the business letter (us as clients), we split up the sections and wrote them individually | Complete business letter | All team members | 2016-10-13
Attendance: Matthew, Veronica, Reeve, Samuel, Hayden

## 17-10-2016
Meeting Minutes
Date:17/10/2016 | Week 12
Agenda Items | Discussion Points | Action Required | Assigned Person | Due Date
Check in | We met as a group showed the team the work completed thus far.
Continue working on Story | We individually continued working on our assigned story, bouncing ideas off each other to improve and unify the website.
Stories Due | - | Complete work for story | All team members | 2016-10-24
Attendance: Matthew, Veronica, Reeve, Samuel, Hayden

## 24-10-2016
Meeting Minutes
Date:24/10/2016 | Week 13
Agenda Items | Discussion Points | Action Required | Assigned Person | Due Date
Demonstrate work to clients | We met with out clients and demonstrated work completed in Release 2 / Sprint 4